## Sheet1
PW Team
Job No | Site | Surveyor | TL | Stage of Scheme (On site/ EOD) | Client | Contractor | Total No Units | No. of flats | Flat Entrance Door Manufacturer | Comments
14/111 | Rifle Range Farm, Hartley, Wintney | PW | PW | Defects | Vivid | Bewley | 38 | 2 | Premdor | Plot 30 and 31, email sent for clairification 20/08, Premdor details provided. Premdor door sets have not been affected
15/080 | Queens Road, Bisley | PW | PW | Defects | Vivid | Redrow | 44 | 11 | IG Doors | Snowdon units plots 100-110, end of defects inspection already undertaken. Block just out of defects, no making good cert has yet been issued.
16/007 | Portsmouth Road | PW | PW | Site | TVHA | Beechcroft | 20 | 20 | Premdor | TS10 Fire resisting door with non metalic leaves - (All 20no. Plots on development), email sent for clairification 20/08, email received 24/08/2018 confirming that the doors on this site are not affected
16/008 | Stane Street | PW | PW | Site | Clarion | Cala | 43 | 12 | Stairway Joinery (Midlands) | Plots 22-25, 45-46, 52-56, 74-75 affected, email sent for clairification 20/08, update received that the doors specified are timber doors and unlikely to be affected by recent issues
16/056 | Ashford Road, Harrietsham | MH | PW | Defects | Circle | Barratts | 44 | 27 | Ian Firth or IG Doors | Plots 1-8, 73-79, 84-90 & 99-103 - EOD 23/08/2018
16/093 | Ryarsh Park | MH | PW | Defects | Circle | Redrow | 27 | 12 | IG Doors | Plots 81-92 EOD 20/02/2019
16/105 | St Andrews Park (Ph 4) | MH | PW | Defects | Optivo | Redrow | 44 | 21 | IG Doors | Plots 365-385 EOD 16/06/2019
17/001 | Ebbsfleet Green, Ebbafleet (Ph B) | MH | PW | Defects | Moat | Redrow | 27 | 18 | IG Doors | Plots 47-55 & 65-82 EOD 26/03/2019
17/002 | Ebbsfleet Green, Ebbsfleet (Ph C) | MH | PW | Site | Moat | Redrow | 18 | 18 | IG Doors | Plots 181-198 Doors have not been ordered, awaiting Contrractors Proposal
17/034 | Sandy Lane, Waltham Chase | MH | PW | Site | Vivid | Linden | 25 | 6 | IG Doors | Plots 10-15, products previously circulated by VIVID Not used, IG Doors confirmed. These have been installed to ground and first floor but not top floor flats. HS awaiting update from Technical team Tuesday 28/08/2018 for course of action to replace doors
17/065 | Whyteleafe, Godstone Rd | PW | PW | Site | Clarion | Haxted | 16 | 16 | TBC | all 16 plots within block E, doors not installed to units. Plots will not be affected due to stage of build. Door info circulated by David Willson, it appears that no issues are recorded and existing manufacturers identified are not used on this site.
17/079 | Stane Street, Pulborough (PD units) | PW | PW | Site | Clarion | Cala | 76 | 6 | Stairway Joinery (Midlands) | plot 76-81, email sent for clairification 20/08, update received that the doors specified are timber doors and unlikely to be affected by recent issues
17/117 | Manor Park, Mierscourt | MH | PW | Site | MHS | Redrow | 34 | 18 | Premdor | Plots 14-23 & 26-34 - Contractor has propsed a timber door in lieu of IG Doors
JL Team
Job No | Site | Surveyor | TL | Stage of Scheme (On site/ EOD) | Client | Contractor | Total No Units | No. of flats | Flat Entrance Door Manufacturer | Comments
17/097 | Nugent Close, Dunsfold | AH | PW | Site | Vivid | Vanderbilt | 17 | 8 | 17/08/18 emailed CB (Vanderbilt Carl Berwick) Awaiting response | FED open to external areas - no communal - on site. Plots 6,7,9,10,19,20,24,25 Flats with external facing doors - no communal area Plots 3,4,5,8,11,12,18,21,22,23
14/052 | Dunmow Road | JL | JL | Defects | CHP | Bovis | 40 | 15 | Premdoor Crosby Ltd | Scheme has 2no. Blocks of flats, 11no. And 4no.
14/114 | Blackhorse Road | JL | JL | Defects | Settle | Barratts | 63 | 36 | IG Doors | Scheme has 2no. Blcos of 18no. Flats. Chasing contractor for update on their proposals around this scheme.
15/027 | Foundation House | JL | JL | Defects | Clarion | Redrow | 10 | 10 | Nationwide | Scheme of 10no. Flats in Block D.
17/068 | Foreman Road | JL | JL | Site | Mountgreen | Thakeham | 9 | 4 | IG Doors | Scheme on site, Thakeham advised they are currently sourcing a new door manufacturer and will advise once agreed.
17/109 | Arisdale Avenue | JL | JL | Site | CHP | Bellway | 11 | 11 | Jeld-Wen | Bellway have confirmed spec.
15/109 | Matthews Green Farm (Phase2a) | AH | JL | SIte | TVHA | Bovis | 82 | 24 (Plots 1-12 & 67-78) | CF198 FD30 Premdor Moulded 57267- Flush Prem FD30 - CF240A 58665- Flush Vicaima - CF218 | List of 3 doors issued by Bovis following request from Client regarding information on details of fire doors. Bovis Technical team have been requested to send info into locations. Last 12 handovers being achieved 21/8/18 on plots 67-78
16/048 | Matthews Green Farm (Phase1) | AH | JL | Defects | TVHA | Bovis | 23 | 15 (Plots 1-11 & 17-20) | CF198 FD30 Premdor Moulded 57267- Flush Prem FD30 - CF240A 58665- Flush Vicaima - CF218 | List of 3 doors issued by Bovis following request from Client regarding information on details of fire doors. Bovis Technical team have been requested to send info into locations. DLP Period until October 2018 Plots 1-11 Flats with communal areas Plots 17-20 Flats with communal areas Plots 21-24 Houses
15/117 | The Ridings, Sudbury on Thames | AH | JL | EOD | PA Housing | CALA Homes | 14 | 10 | 24/08/18 emailed GT (CALA Grant Tonks) Awaiting response | DLP Period - final inspection completed - 6/4/18 Flats 16-21 with communal area Plots 22-25 with FED to external - no communal area Houses 14-15
17/020 | Matthews Green Farm (Phase 2B & 3) | AH | JL | Site | VIVID | Linden Homes | 16 | 7 | Internal Flat entrance doors - Premdor Communal Flat entrance door - IG Doors | Plots 10-16 Flats with Communal areas Houses - Plots 1-9
2017/087 | Becketts Rise, Worting Farm | AH | JL | Site/PC | VIVID | Redrow | 28 | 8 | IG Doors | Raised at Aug 2018 Progress Meeting - Redrow have confirmed that they will replace the doors. - updated spec & programme of these works to be provided. Plots 21-24 & 31-34 Flats with communal areas 13-20 & 43-54 Houses/Bungalows Plots 21-24 achieved PC on 28/6/18
2017/052 | Kings Road, West End Woking | AH | JL | Site | CHG | Thakeham | 14 | 8 | 24/08/18 emailed CW (Thakeham Homes - Clive Wright) Awaiting response | Plots 22&23 have communal stairwell to FED - 19,20,21,24,25,26,27 all other flats have FED to external areas - no communal area. Houses 4,5,6,33,34
IS Team
Job No | Site | Surveyor | TL | Stage of Scheme (On site/ EOD) | Client | Contractor | Total No Units | No. of flats | Flat Entrance Door Manufacturer | Comments
2012/001 | East Berkshire College, Maidenhead, Berkshire | GC | IS | EOD | Housing Solutions | Linden Homes | 19 | 14 | Vicaima Dekadoor | Fire ratings shown on architects drawings/door schedule
2013/067 | Three Rivers, Leavesden | GC | IS | EOD | Home Group | Bovis Homes | 35 | 18 | Jeldwen Atherton | Page 67 & 68 of contract document
2014/020 | Verney Road, Aylesbury (Phase 3) | GC | IS | EOD | VAHT | Bloor Homes | 12 | 6 | ?
2012/107 | Kentwood Farm, Wokingham | GC | IS | EOD | Housing Solutions | Crest Nicholson | 81 | 38 | Vicaimia Dekadoor | Page 3 of specification
2014/139 | Daws Hill, High Wycombe- TVHA | GC | IS | EOD | TVHA | Taylor Wimpey | 30 | 13 | ? | DR has requested info from Oliver Battershaw
2016/117 | Reading Gateway, Reading | GC | IS | On Site | Sovereign | Bewley Homes | 52 | 33 | Premdor | Confirmed in an email from Bob Saund (23/08)
2017/022 | Mill Lane, Calcot | GC | IS | On Site | Sovereign | Bellway | 18 | 8 | Premdor | Page 9 of specification
2017/064 | Manor Farm , Drayton, Abingdon | GC | IS | On Site | SOHA | Cala Homes | 20 | 4 | Premdor or Jeldwen | Page 50 of Contract Document (Specification)
2017/089 | Hadden Hill, Didcot | GC | IS | On Site | SOHA | Bovis Homes | 29 | 9 | National Hickman | Page 48 of Contract Document (Specification)
2017/098 | Oak Hill, Crowell Road, Chinnor | GC | IS | On Site | Sovereign | Bellway | 48 | 12 | IG Doors | Page 3 of Spec Review
TH Team
Job No | Site | Surveyor | TL | Stage of Scheme (On site/ EOD) | Client | Contractor | Total No Units | No. of flats | Flat Entrance Door Manufacturer | Comments
TH Projects
08/115 | 108 Bethune Rd, Stoke Newington, N16 | TH | TH | Outside EOD NMGD to be issued | Family Mosaic | Mulalley & Co. | 39 | 39
09/100 | Menorah School, Wembley, Middlesex | TH | TH | Outside EOD NMGD to be issued | Network Homes | Kier | 160 | 142
11/011 | 165-169 Merton Rd, Merton - TVHA | TH | TH | Outside EOD NMGD to be issued | TVHA | Austins in Administration | 9 | 9
AM/17/080 | Green Lane, Eltham | GS | TH | On Site | Hexagon | Devcon | 12 | 12 |  | Clerk of Works (EA Martin Arnolds)
AM/18/023 | 21-23 Watling Street, Bexleyheath | GS | TH | On Site | Hexagon | ICG | 16 | 16 |  | Clerk of Works (EA Potter Raper)
BC Projects
AM/13/091 | Church Lane, Deal | BC | TH | EOD | Orbit | Persimmon | 69 | 18 |  | Blocks A, B and C
AM/14/069 | Forster House, Whitefoot Lane | BC | TH | On Site | Phoenix Community Housing | Saltash | 22 | 22
AM/14/084 | The Sawyers Arms, Ashford Road Feltham | BC | TH | EOD | A2D | Syntec | 24 | 20
AM15/052 | Union Close, Leytonstone, E11 | BC | TH | On Site | Peabody | Engie | 79 | 65
AM/18/010 | 1-5 Dorset Close, NW1 | BC | TH | On Site | A2D | Syntec | 12 | 12
HS Projects
AM/2017/141 | Odeon Parade, Ealing - EA | HS | TH | On site (S106 pre contract) | RHP | Henry Construction | 14 | 14 | tbc | Whilst works are progressing on site, the specification remains top be agreed and contracts exchanged with RHP
Note on K3: Phil Wilsdon: